## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Workspace setup and authentication (Landing/Login, JWT, password handling) | MUST HAVE | No Dependency | Madhu | 3- Completed
S2 | S2 | US-002 | Feedback data ingestion and upload workflow | MUST HAVE | US-001 authentication and database | Devendra P | 3- Completed
S3 | S3 | US-003 | Analytics, EDA and trend analysis services | MUST HAVE | US-002 ingestion pipeline | Madhu, Devendra P | 3- Completed
S4 | S4 | US-004 | Theme extraction, sentiment, pain-point and preprocessing analysis | MUST HAVE | US-003 analytics services | Dhanuja | 3- Completed
S5 | S5 | US-005 | Feature request extraction and feedback service integration | SHOULD HAVE | US-002, US-004 | Dhanuja | 3- Completed
S6 | S6 | US-006 | Feature prioritization workflow and prioritization view | MUST HAVE | US-005 feature requests | Ankita P | 3- Completed
S7 | S7 | US-007 | PRD generator for converting prioritized features into product requirements | SHOULD HAVE | US-006 prioritization | Ankita P | 3- Completed
S8 | S8 | US-008 | Roadmap generation and roadmap workspace | SHOULD HAVE | US-007 PRD generation | Devendra P | 3- Completed
S9 | S9 | US-009 | AI Copilot conversational assistance and chat interface | SHOULD HAVE | US-003 to US-008 | Madhu | 3- Completed
S10 | S10 | US-010 | Dashboard, reports and product insights visualization | MUST HAVE | US-003, US-004 | Dhanuja | 3- Completed
S10 | S10 | US-011 | User stories, feedback management and application settings | MUST HAVE | US-002, US-005 | Ankita P | 3- Completed
S10 | S10 | US-012 | Backend API, CRUD, schemas and frontend-backend integration | MUST HAVE | US-001 to US-011 | Madhu, Dhanuja, Devendra P | 3- Completed
S10 | S10 | US-013 | End-to-end validation, integration testing and deployment readiness | MUST HAVE | All modules | Devendra P, Madhu, Dhanuja, Ankita P | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Devendra P03 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 286 | 55 | 63 | 69 | 57 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Create workspace landing and login pages | 2026-06-25 | 2026-06-29 | Dhanuja | Design | 3- Completed | 6 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 0; Day 5: 0
US-001 | 2 | Implement JWT handler and password utilities | 2026-06-25 | 2026-06-30 | Madhu | Coding | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 0
US-001 | 3 | Set up authentication dependencies and user model | 2026-06-25 | 2026-07-01 | Devendra P | Coding | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
US-001 | 4 | Integrate header, sidebar and application context | 2026-06-25 | 2026-07-01 | Ankita P | Build | 3- Completed | 6 | Day 1: 1; Day 2: 1; Day 3: 2; Day 4: 1; Day 5: 1
SPRINT 2 BACKLOG
US-002 | 1900-01-04 | Build data upload interface and feedback ingestion flow | 2026-07-02 | 2026-07-08 | Dhanuja | Build | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 1; Day 5: 1
US-002 | 1900-01-05 | Implement upload API and request validation | 2026-07-02 | 2026-07-07 | Devendra P | Coding | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 0
US-002 | 1900-01-06 | Implement preprocessing and cleaning service | 2026-07-02 | 2026-07-08 | Madhu | Coding | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
US-002 | 1900-01-07 | Connect ingestion workflow to database CRUD | 2026-07-02 | 2026-07-08 | Ankita P | Integration Test | 3- Completed | 6 | Day 1: 1; Day 2: 1; Day 3: 2; Day 4: 1; Day 5: 1
SPRINT 3 BACKLOG
US-003 | 1900-01-08 | Implement EDA service and analytics calculations | 2026-07-09 | 2026-07-15 | Madhu | Coding | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
US-003 | 1900-01-09 | Implement trend analysis service | 2026-07-09 | 2026-07-15 | Ankita P | Coding | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
US-003 | 1900-01-10 | Expose analytics API endpoints | 2026-07-09 | 2026-07-15 | Devendra P | Build | 3- Completed | 6 | Day 1: 1; Day 2: 1; Day 3: 2; Day 4: 1; Day 5: 1
US-003 | 1900-01-11 | Create analytics module UI and connect data flow | 2026-07-09 | 2026-07-15 | Dhanuja | Build | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
SPRINT 4 BACKLOG
US-004 | 1900-01-12 | Implement theme extraction and embeddings service | 2026-07-16 | 2026-07-22 | Dhanuja | Coding | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
US-004 | 1900-01-13 | Implement sentiment analysis and pain-point detection | 2026-07-16 | 2026-07-22 | Madhu | Coding | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
US-004 | 1900-01-14 | Build validation and preprocessing integration | 2026-07-16 | 2026-07-22 | Devendra P | Integration Test | 3- Completed | 6 | Day 1: 1; Day 2: 1; Day 3: 2; Day 4: 1; Day 5: 1
US-004 | 16 | Create theme extraction UI module | 2026-07-16 | 2026-07-22 | Ankita P | Build | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
SPRINT 5 BACKLOG
US-005 | 17 | Implement feature request extraction service | 2026-07-23 | 2026-07-29 | Madhu | Coding | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 1; Day 5: 1
US-005 | 18 | Implement feedback service and feedback model integration | 2026-07-23 | 2026-07-29 | Devendra P | Coding | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
US-005 | 19 | Create feature request module UI | 2026-07-23 | 2026-07-29 | Dhanuja | Build | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
US-006 | 20 | Build feature prioritization workflow and view | 2026-07-23 | 2026-07-29 | Ankita P | Build | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
SPRINT 6 BACKLOG
US-006 | 21 | Refine prioritization rules and service integration | 2026-07-30 | 2026-08-05 | Ankita P | Coding | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 1; Day 5: 1
US-007 | 22 | Design PRD generator workflow and output structure | 2026-07-30 | 2026-08-05 | Devendra P | Design | 3- Completed | 6 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1
US-007 | 23 | Implement PRD generator module UI | 2026-07-30 | 2026-08-05 | Madhu | Build | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
US-007 | 24 | Connect PRD generation to prioritized feature data | 2026-07-30 | 2026-08-05 | Dhanuja | Integration Test | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
SPRINT 7 BACKLOG
US-008 | 25 | Design roadmap generation workflow | 2026-08-06 | 2026-08-12 | Devendra P | Design | 3- Completed | 6 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1
US-008 | 26 | Implement roadmap module UI | 2026-08-06 | 2026-08-12 | Dhanuja | Build | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
US-008 | 27 | Integrate roadmap data with PRD output | 2026-08-06 | 2026-08-12 | Madhu | Integration Test | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
US-008 | 28 | Validate roadmap prioritization and sequencing | 2026-08-06 | 2026-08-12 | Ankita P | System Test | 3- Completed | 6 | Day 1: 1; Day 2: 1; Day 3: 2; Day 4: 1; Day 5: 1
SPRINT 8 BACKLOG
US-009 | 29 | Design AI Copilot interaction flow | 2026-08-13 | 2026-08-19 | Madhu | Design | 3- Completed | 6 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1
US-009 | 30 | Implement chat interface and application integration | 2026-08-13 | 2026-08-19 | Madhu | Coding | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
US-009 | 31 | Connect Copilot context to product insights | 2026-08-13 | 2026-08-19 | Devendra P | Integration Test | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
US-009 | 32 | Validate Copilot responses and UI states | 2026-08-13 | 2026-08-19 | Ankita P | System Test | 3- Completed | 6 | Day 1: 1; Day 2: 1; Day 3: 2; Day 4: 1; Day 5: 1
SPRINT 9 BACKLOG
US-010 | 33 | Implement dashboard module and dashboard API | 2026-08-20 | 2026-08-20 | Dhanuja | Build | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2
US-010 | 34 | Build reports and insights views | 2026-08-20 | 2026-08-20 | Ankita P | Build | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 2
US-011 | 35 | Complete user stories, settings and feedback views | 2026-08-20 | 2026-08-20 | Madhu | Coding | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 1
US-012 | 36 | Integrate frontend modules with backend APIs | 2026-08-20 | 2026-08-20 | Devendra P | Integration Test | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2
SPRINT 10 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Devendra P03 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Devendra P03 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Devendra P03 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Devendra P03 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Devendra P03 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Devendra P03 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZQ4 Devendra P03 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on P3: ====== ID#AAABcShYZRY Devendra P03 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Devendra P03 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Authentication flow and JWT integration needed clarification | Reviewed JWT flow, password handling and API dependencies as a team.
Sprint 2 | Day 4 | Feedback upload validation and ingestion sequencing | Aligned upload, preprocessing, validation and database steps.
Sprint 3 | Day 2 | Analytics outputs required consistent input data | Standardized ingestion outputs before running EDA and trend analysis.
Sprint 4 | Day 4 | Theme, sentiment and pain-point outputs needed common structure | Defined common service output format and validated sample feedback.
Sprint 5 | Day 3 | Feature request extraction needed clear prioritization inputs | Mapped extracted requests to the prioritization workflow.
Sprint 6 | Day 4 | PRD generation requirements were still evolving | Reviewed PRD structure and connected it to prioritized features.
Sprint 7 | Day 3 | Roadmap sequencing depended on PRD information | Defined roadmap inputs, sequencing rules and validation checks.
Sprint 8 | Day 4 | AI Copilot context integration was complex | Held an integration review for chat context and product insights.
Sprint 9 | Day 3 | Dashboard integration required data from multiple services | Verified API responses and aligned dashboard/reporting data.
Sprint 10 | Day 2 | Cross-module integration and validation defects | Created a shared defect-fix list and scheduled end-to-end verification.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-25 | 2026-07-01 | Devendra P, Madhu | Documenting authentication flows before coding | Starting implementation before confirming dependencies | Collaborating on API and UI integration | Reviewed authentication dependencies and completed the core login/workspace flow.
2 | Sprint 2 | 2026-07-02 | 2026-07-08 | Madhu, Dhanuja | Validating uploaded feedback early | Delaying validation until the end of ingestion | Testing data flow with sample feedback | Aligned upload, cleaning and ingestion steps using representative data.
3 | Sprint 3 | 2026-07-09 | 2026-07-15 | Madhu, Dhanuja | Checking analytics results against input data | Using inconsistent test datasets | Reviewing analytics calculations together | Standardized sample inputs and verified EDA and trend outputs.
4 | Sprint 4 | 2026-07-16 | 2026-07-22 | Dhanuja, Ankita P | Reviewing AI analysis outputs with the UI | Treating service and UI work as separate activities | Keeping service contracts consistent | Validated theme, sentiment and pain-point outputs before UI integration.
5 | Sprint 5 | 2026-07-23 | 2026-07-29 | Ankita P, Devendra P | Mapping feature requests to product decisions | Leaving prioritization assumptions undocumented | Using feedback-driven prioritization | Connected extracted feature requests with the prioritization workflow.
6 | Sprint 6 | 2026-07-30 | 2026-08-05 | Devendra P, Madhu | Breaking PRD work into smaller deliverables | Taking on large UI/API changes in one step | Reviewing generated product requirements together | Defined the PRD structure and connected it to prioritized features.
7 | Sprint 7 | 2026-08-06 | 2026-08-12 | Ankita P, Madhu | Testing roadmap sequencing with sample data | Changing roadmap rules without documenting them | Reviewing roadmap output as a team | Validated roadmap inputs and sequencing against PRD information.
8 | Sprint 8 | 2026-08-13 | 2026-08-19 | Madhu, Devendra P | Testing Copilot context incrementally | Waiting until the end to test chat integration | Collaborating on context and UI behavior | Integrated the chat interface and reviewed Copilot context handling.
9 | Sprint 9 | 2026-08-20 | 2026-08-26 | Dhanuja, Ankita P | Checking dashboard data against API responses | Polishing UI before confirming data contracts | Using shared API validation during integration | Aligned dashboard/reporting views with backend service responses.
10 | Sprint 10 | 2026-08-27 | 2026-09-02 | Devendra P, Madhu, Dhanuja, Ankita P | Running end-to-end validation earlier | Accumulating cross-module defects | Maintaining shared review and defect tracking | Started final integration checks and created a common defect-fix/review cycle.
Task Distribution Cut-off | 20/08/2026 | Task distribution is limited to yesterday; no future allocation is included.

## Defect_Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Devendra P | 2026-06-26 | Login request was not accepted correctly when authentication dependency configuration was incomplete | Sprint 1 | Devendra P | Standards | Updated authentication dependency/configuration and retested login | 2026-06-27 | Closed | Retested valid and invalid login flow.
2 | Madhu | 2026-07-03 | Invalid feedback upload data was not being rejected with a clear validation message | Sprint 2 | Madhu | User Interface | Added clearer upload validation handling and error messaging | 2026-07-04 | Closed | Invalid upload case verified.
3 | Dhanuja | 2026-07-10 | Analytics output changed when inconsistent input datasets were used | Sprint 3 | Dhanuja | Logical | Standardized input preprocessing before analytics execution | 2026-07-11 | Closed | EDA and trend analysis retested with cleaned data.
4 | Ankita P | 2026-07-17 | Theme and sentiment service outputs were not using a consistent response structure | Sprint 4 | Dhanuja | Logical | Aligned service response fields and updated consuming UI logic | 2026-07-18 | Closed | Theme, sentiment and pain-point outputs verified.
5 | Madhu | 2026-07-24 | Extracted feature requests were not mapped consistently to prioritization inputs | Sprint 5 | Ankita P | Logical | Mapped feature request fields to the prioritization workflow | 2026-07-25 | Closed | Prioritization flow retested.
6 | Devendra P | 2026-07-31 | PRD generation required a consistent input structure from prioritized features | Sprint 6 | Devendra P | Standards | Defined and validated the PRD input/output structure | 2026-08-01 | Closed | PRD output verified with prioritized feature data.
7 | Ankita P | 2026-08-07 | Roadmap sequencing did not consistently reflect PRD information | Sprint 7 | Ankita P | Logical | Updated roadmap sequencing and validated dependencies | 2026-08-08 | Closed | Roadmap sequence retested.
8 | Madhu | 2026-08-14 | AI Copilot context was not consistently available to the chat workflow | Sprint 8 | Madhu | Logical | Updated context integration between product insights and Copilot | 2026-08-15 | Closed | Chat context flow retested.
9 | Dhanuja | 2026-08-20 | Dashboard/reporting data required alignment across multiple backend services | Sprint 9 | Dhanuja | Logical | Aligned API response handling and dashboard data mapping | 2026-08-20 | Closed | Dashboard and reports verified with service data.

## Unit_Test_Plan
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
1 | Workspace landing page | Open the application and navigate to the landing page | Landing page route loads without an error | Landing page is displayed with workspace/login options | Pass
2 | User login | Enter valid user credentials and submit login | Valid username/password are supplied | User is authenticated and redirected to the application | Pass
3 | Invalid login handling | Enter invalid credentials and submit login | Invalid username/password are supplied | Login is rejected and an appropriate error is shown | Pass
4 | JWT token handling | Authenticate and inspect the authenticated request flow | Valid login session is created | JWT is generated/handled and authenticated requests are accepted | Pass
5 | Password utility | Create/check a password using the password utility | Valid password is supplied | Password handling completes and the credential is not stored as plain text | Pass
6 | Feedback upload | Upload a supported feedback dataset | Valid feedback file is selected | File is accepted and ingestion starts successfully | Pass
7 | Upload validation | Upload an unsupported or invalid file | Invalid file/data is supplied | Upload is rejected with a validation message | Pass
8 | Data cleaning | Run the cleaning/preprocessing service on feedback data | Input contains missing/unclean values | Data is cleaned into the expected structure | Pass
9 | Database CRUD | Create, read, update and delete a feedback/user record | Valid record and database connection are available | CRUD operations complete successfully | Pass
10 | EDA analytics | Run EDA on ingested feedback | Valid cleaned feedback data is available | EDA metrics/results are generated correctly | Pass
11 | Trend analysis | Run trend analysis on feedback over time | Feedback contains valid date/time information | Trend output is generated for the available periods | Pass
12 | Theme extraction | Run theme extraction on feedback text | Valid feedback text is available | Relevant themes are extracted and returned | Pass
13 | Sentiment analysis | Run sentiment analysis on feedback text | Valid feedback text is available | Each applicable feedback item receives a sentiment result | Pass
14 | Pain-point detection | Run pain-point analysis on customer feedback | Feedback contains problem-related statements | Pain points are identified in the analysis output | Pass
15 | Embeddings service | Generate embeddings for supported feedback text | Valid text input is supplied | Embeddings are generated without a service error | Pass
16 | Feature request extraction | Process feedback containing feature requests | Feedback includes feature-request statements | Feature requests are extracted and structured | Pass
17 | Feature prioritization | Open prioritization view and prioritize extracted features | Feature request data is available | Features can be prioritized and the selected priority is retained | Pass
18 | PRD generator | Generate a PRD from a prioritized feature | A prioritized feature is available | PRD content is generated with the expected product requirements | Pass
19 | Roadmap generation | Generate a roadmap from prioritized/PRD information | Valid prioritized product information is available | Roadmap items are generated in an understandable sequence | Pass
20 | AI Copilot chat | Open Copilot and send a product-related question | Copilot is available and valid prompt is supplied | A relevant response is returned in the chat interface | Pass
21 | Dashboard | Open dashboard and load product insights | Analytics data is available | Dashboard loads metrics and visual insights correctly | Pass
22 | Reports view | Open reports and review generated product insights | Report data is available | Reports display the expected analysis/results | Pass
23 | User stories view | Open user stories module and review/create a story | Valid product story information is supplied | User story is displayed/saved in the expected format | Pass
24 | Settings view | Open settings and update an available setting | User is authenticated | Setting is updated and reflected after save | Pass
25 | End-to-end integration | Upload feedback and execute the workflow through analytics, prioritization and product outputs | All dependent services are available | Data flows across modules without blocking integration errors | Pass